## Slide 1: Team 15: Rogue Chess App Bi-Weekly Update 2 Jose Herrera, Travis Head Sponsor: Pranav Dhulipala TA: Eric Robles
Notes: Michelle

## Slide 2: Project Summary
Problem: There are many variations of the game of chess; however, after a while it can be predictable or lack of excitement.
Proposed Solution: Develop an app of a new chess variation with a randomization factor for Android products.
  Develop an AI for Single Player Mode
  Create a randomization factor
  Create a User Interface for the players interaction
  Highlighted boxes to assist the player in making the next move legally
  Create different difficulty levels
  Upload the contents to the cloud
Notes: Kyle

## Slide 3: Project Overview
Notes: Eric

## Slide 4: Project Timeline
__ - Completed
__ - In Progress
- Not Started
Subsystem Corrections (to complete by 9/19) | Research for Server Integration (completed 9/12) | Connection of Game App to Server (to complete by 9/20) | Connection of AI & App to Server (to complete by 9/26) | Final Integration (to complete by 10/17) | System Test & Optimization (to complete by 10/31) | Validation (to complete by 11/21) | Demo and Report (to complete by 11/28)
Notes: Eric

## Slide 5: Game Functionality and User Interface Jose Herrera
Accomplishments since last presentation 12 hrs of effort | Ongoing progress/problems and plans until the next presentation
Changed all the backgrounds/text color and button colors for better user Connected the App to the Firebase Cloud System for the AI and Application Integration Wrote test code in order to test the firebase cloud storage is working | Finish Castling Code Finish Randomization

## Slide 6: Game Functionality and User Interface Jose Herrera

## Slide 7: Game Functionality and User Interface Jose Herrera

## Slide 8: Artificial Intelligence Travis Head
Accomplishments since last presentation 18 hrs of effort | Ongoing progress/problems and plans until the next presentation
Researched Deploying AI into Firebase Completed Base Code for Integration Redesigned Model of Neural Network | Discussing Server Access Keys Deploying AI to the Server Updated AI Needs Retraining

## Slide 9: Artificial Intelligence Travis Head

## Slide 10: Execution Timeline
Notes: Michelle

## Slide 11: Execution & Plan
Notes: Michelle

## Slide 12
Questions?